## Service Quote Slab Elevation
| Tel. 877.390.5438 |  | Home/Flood Map Description
| gc@excellohomes.com |  | Footprint of Home | 2314 | Total Sq Footage | 2314
| www.excellohomes.com |  |  |  | Elevate (DFE) ft. | 6.5
[5 empty] | Freeboard ft. | 2
| Elevation Proposal for: |  |  | 0 | Total Elevation ft. | 8.5
| Henry & Gloria Blair |  |  | 0 | Elevation Type | Slab Elevation
| 18727 Martinique Drive |  | Relocation Days | 120
| Nassau Bay, TX 77058 |  | Draw #1 AMOUNT: |  |  | 55440.73
| 713.443.6321 713.443.7904 |  | 120 Days of Living Allowance
| ITEM # | WORK DESCRIPTION |  | QTY | PRICE/UNIT | PRICE
PRE-CONSTRUCTION
| 1 | Engineering - Drawings, Inspections, TWIA Submittals, Required Architectural Plans |  | 1 |  | 20%
| 2 | Home Inspection - photograph and document pre-existing condition of home |  | 1 |  | 100%
| 3 | Surveys - Elevation Certificate Pre-lift, Post-lift, and Final Elevation Certificate |  | 1 |  | 20%
4
5
SITE PREPARATION
| 6 | Mobilization, Site Prep (includes breaking up and the removal and disposal of concrete), Equipment, Supervision, Labor |  | 1 |  | 100%
| 7 | Remove existing landscaping required for elevation, it is the homeowners obligation to maintain landscaping removed, installation of Silt fence |  | 1 |  | 0%
| 8 | Site toilet, dumpster and hauling off debris |  | 1 |  | 20%
9
| 10 | Tree Removal (Regular) |  |  |  | 0%
| 11 | Tree Removal (Large) |  |  |  | 0%
| 12 | Tree Trimming |  |  |  | 0%
EXCAVATION, PILES, ELEVATION
| 13 | Tunneling/Excavating (lnft) to faciltate the installation of 8"x8" concrete pilings |  | 289 |  | 0%
| 14 | Raise, Shore and Align above mentioned residence to satisfy BFE and local free board requirements; according to engineer specifications. Contractor to provide all block, shims, and angle iron, or any other materials required during lift. |  | 2314 |  | 0%
15
16
17
18
FOUNDATION
| 19 | Install 8"x8" concrete pillings to support the existing concrete slab under residence to the point of refusal, where engineer has specified to provide sufficient weight load support. |  | 72 |  | 0%
| 20 | Pour 24"X24" continuous reinforced concrete footer as per engineer specifications |  | 327 |  | 0%
| 21 | Install 16" X 16" pialister block concrete column with four (4) #5 rebar tied into footings and original slab with epoxy for structural support in accordance with engineer specifications. (columns will be pumped solid with concrete using pump truck to avoid cold joints) |  | 29 |  | 0%
| 22 | Labor and material to install painted steel beams WF 8" x 18#/ft. to span areas for interior columns per engineered specifications |  | 6 |  | 0%
23
| 24 | Pour concrete slab under raised home per engineered specifications. Price includes pump truck as required. Install three (3) sided CMU block wall with required flood vents. This includes the required rebar and concrete fill as required by Engineer Specifications. |  | 2314 |  | 0%
UTILITIES
| 25 | Disconnect and reconnect/repair water, sewer / septic, gas as required by local building agencies |  | 1 |  | 0%
| 26 | Disconnect, Raise and reconnect A/C system(s) to new elevated height requirements |  | 1 |  | 0%
| 27 | Disconnect and reconnect electrical as required by local building agencies |  | 1 |  | 0%
STEPS, LANDINGS, CARPENTRY
28
| 29 | Construct 4'X4' landing to meet program requirements (including stairs and handrails)A raise height above 12 feet will require a landing as per code; larger and increased number of support posts. |  | 1 |  | 0%
| 30 | Construct 4'X8' landing to meet program requirements (including stairs and handrails)A raise height above 12 feet will require a landing as per code; larger and increased number of support posts. |  | 1 |  | 0%
| 31 | It is more cost effective to connect egress points with a 4' walkway than construct multiple stairways |  |  |  | 0%
FINISHES AND LANDSCAPING
| 32 | Equipment, dirt and labor to allow for proper grading as required by local agencies |  | 1 |  | 0%
| 33 | Pallets of Sod with labor and installation |  | 4 |  | 0%
| 34 | Detach and reset fence; included in bid price |  |  |  | 0%
| 35 | Extend gutter to ground level; included in bid price |  |  |  | 0%
| 36 | Repair existing sprinkler system after completion of elevation, included in bid price |  |  |  | 0%
| 37 | Post site cleanup |  | 1 |  | 0%
| 38 | Spray foam insulation underneath elevated slab (closed cell insulation =Minimum of R-13) |  | 2314 |  | 0%
| 39 | Repair / replace concrete damaged during elevation (sqft.) |  | 250 |  | 0%
| 40 | Add Wood Handrails to Elevated Porch Area /Deck |  |  |  | 0%
| 41 | Detach breezeway and properly repair roofline and Home |  |  |  | 0%
| 42 | Warranty, Supervison,Overhead |  |  |  | 20%
ADA Approved Items
| 43 | ADA Personal Lift |  | 1 |  | 0%
Eligible Elevation Costs
Bonding & Insurance
ss |  | Draw #1 Amount |  |  |  | 55440.73

## Bid Template
BID TEMPLATE
| Contractor: | Excello Homes |  | 1st Floor sqft | 2314
| Homeowner: | Henry & Gloria Blair |  | 2nd Floor sqft | 0
| Address: | 18727 Martinique Drive |  | Total sqft | 2314
| City: | Nassau Bay, TX 77058 |  | BFE | 0
|  |  |  | Floor Elevation | 0
| Foundation Type: | Slab Elevation |  | Freeboard | 2
|  |  |  | Target BFE | 6.5
|  |  |  | Total Elevation | 8.5
Item | Description |  | QTY | Unit Price | Price
Pre-Construction Activites
1 |  |  | 1 | 1.4 | 1.4
SUBTOTAL |  |  |  |  | 1.4
Site Preparation/Development
2 |  |  | 1 | 1.2 | 1.2
SUBTOTAL |  |  |  |  | 1.2
Excavation, Pilings, Elevation
3 |  |  | 1 | 0 | 0
SUBTOTAL |  |  |  |  | 0
Foundation
4 |  |  | 1 | 0 | 0
SUBTOTAL |  |  |  |  | 0
Utilities
5 |  |  | 1 | 0 | 0
SUBTOTAL |  |  |  |  | 0
Flatwork
6 |  |  | 1 | 0 | 0
SUBTOTAL |  |  |  |  | 0
Steps, Landings, and Carpentry
7 |  |  | 1 | 0 | 0
SUBTOTAL |  |  |  |  | 0
Finish-Outs and Landscaping
8 |  |  | 1 | 0.2 | 0.2
SUBTOTAL |  |  |  |  | 0.2
ADA Approved Items
9 |  |  | 1 | 23500 | 23500
SUBTOTAL |  |  |  |  | 23500
| Subtotal Grant Eligible Costs |  |  |  | 23502.8
10 | Bonding and Insurance |  |  |  | 0
11 | Profit and Overhead |  |  |  | 0
12 | Sales Tax on Materials |  |  |  | 0
13 | Permiting Fee |  |  |  | 0
GRANT ELIGIBLE COSTS TOTAL |  |  |  |  | 23502.8
Owner Paid Extras (State Approved)
14 | Additional Lift Height 10'-13' |  | 2.25 | 2.25 | 10413
15 | Additional Landing/Decking- Front of Home- | Front of Home | 363 sqft | 25 | 9075
16 | Upgrade - Front of Home-standard metal handrails |  | 198 LF | 65 | 12870
17 | Upgrade toSplitfaced Block Wall |  | 1,440 sqft | 5 | 7200
18 |  |  |  |  | 0
19 |  |  |  |  | 0
SUBTOTAL |  |  |  |  | 39558
TOTAL CONTRACTED PRICE |  |  |  |  | 63060.8

## Info
| Customer Name | Henry & Gloria Blair
| Customer Street Address | 18727 Martinique Drive | Total sqft | 2314
| City, State zip code | Nassau Bay, TX 77058
| Customer Phone# | 713.443.6321 713.443.7904
Customer email
| 1st floor Sq. Ft. | 2314
2nd floor sq. ft.
| Attached Garage sq ft | 0 |  | price per sqft
| Porches sq. ft | 0 |  | 23.9588
| Decks sq ft | 0
| Total foot print sqare footage | 2314
| Elevation Type | Slab Elevation
| Relocation Allowance (days) | 120
| Elevate DFE (ft) | 6.5
| Freeboard (ft.) | 2
| Additional Lift Height | 0
| Total Elevation | 8.5
BFE
| Floor Elevation |  |  | The "x" factor
0.5
ITEM # | WORK DESCRIPTION |  | qty | price/unit
PRE-CONSTRUCTION
1 | Engineering - Drawings, Inspections, TWIA Submittals, Required Architectural Plans |  | 1 | 6500
2 | Home Inspection - photograph and document pre-existing condition of home |  | 1 | 500
3 | Surveys - Elevation Certificate Pre-lift, Post-lift, and Final Elevation Certificate |  | 1 | 1800
4
5
SITE PREPARATION
6 | Mobilization, Site Prep (includes breaking up and the removal and disposal of concrete), Equipment, Supervision, Labor |  | 1 | 6500
7 | Remove existing landscaping required for elevation, it is the homeowners obligation to maintain landscaping removed, installation of Silt fence |  | 1 | 2000
8 | Site tiolet, dumpster and hauling off debris |  | 1 | 3200
9 | Demo masonary stairs |  | 0 | 0
10 | Tree Removal (Regular) |  | 0 | 0
11 | Tree Removal (Large) |  | 0 | 0
12 | Tree Trimming |  | 1 | 1000
EXCAVATION, PILES, ELEVATION
13 | Tunneling/Excavating (lnft) to faciltate the installation of 8"x8" concrete pilings |  | 289.25 | 60
14 | Raise, Shore and Align above mentioned residence to satisfy BFE and local free board requirements; according to engineer specifications. Contractor to provide all block, shims, and angle iron, or any other materials required during lift. |  | 2314 | 10.5
15 | addition expense to lift 2nd floor |  | 1150 | 10
16 | Elevate Existing Deck |  | 0 | 19
17 | Excavate under the exterior and interior load-bearing supports of the residence to prepare for concrete footings in accordance with engineer specifications |  | 1 | 5000
18 | Remove and replace dirt due to location of septic system and/or size of property there is insufficient space to store excavated dirt |  | 0 | 0
FOUNDATION
19 | Install 8"x8" concrete pillings to support the existing concrete slab under residence to the point of refusal, where engineer has specified to provide sufficient weight load support. |  | 79.7931 | 150
20 | Pour 24"X24" continuous reinforced concrete footer as per engineer specifications |  | 321.3889 | 56
21 | Install 16" X 16" pialister block concrete column with four (4) #5 rebar tied into footings and original slab with epoxy for structural support in accordance with engineer specifications. (columns will be pumped solid with concrete using pump truck to avoid cold joints) |  | 39.8966 | 400
22 | Labor and material to install painted steel beams WF 8" x 18#/ft. to span areas for interior columns per engineered specifications |  | 6.6114 | 1100
23 | Additional support for masonary fireplace |  | 0 | 0
24 | Pour concrete slab under raised home per engineered specifications. Price includes pump truct as required |  | 2314 | 10.5
UTILITIES
25 | Disconnect and reconnect/repair water, sewer / septic, gas as required by local building agencies |  | 1 | 5322.2
26 | Disconnect, Raise and reconnect A/C system(s) as needed to new elevated height requirements |  | 1 | 1500
27 | Disconnect and reconnect electrical as required by local building agencies |  | 1 | 6317.22
STEPS, LANDINGS, CARPENTRY
28 | Build temporary stairs for access to home during elevation process |  | 0 | 0
29 | Construct 4'X4' landing to meet program requirents (including stairs and handrails) |  | 2 | 3400
30 | Construct 4'X8' landing to meet program requirents (including stairs and handrails) |  | 0 | 3570
31 | It is more cost effective to connect egress points with a 4' walkway than construct multiple stairways |  | 0 | 25
FINISHES AND LANDSCAPING
32 | Equipment, dirt and labor to allow for proper grading as required by local agencies |  | 1 | 1800
33 | Pallets of Sod with labor and installation |  | 4 | 250
34 | Detach and reset fence |  | 0 | 0
35 | Extend gutter to ground level |  | 0 | 600
36 | Repair existing sprinkler system after completion of elevation |  | 0 | 0
37 | Post site cleanup |  | 1 | 600
38 | Spray foam insulation underneath elevated slab (3 - 4 inches of closed cell insulation =Minimum of R-13) |  | 1500 | 4
39 | Repair / replace concrete damaged during elevation (sqft.) |  | 250 | 10
40 | Add Wood Handrails to Elevated Porch Area /Deck |  | 36 | 25
41 | Detach breezeway and properly repair roofline and Home |  | 0 | 0
42 | Warranty, Supervison, Overhead |  | 1 | 14590
ADA Approved Items
43 | Install personal mechanical lift / platform lift based on elevation height |  | 0
44 | Install enclosed elevator based on elevation height |  | 1
NON Eligible Elevation Costs
| 3rd stop for ADA Lift |  | 0
|  |  | 0 | 0
|  |  | 0 | 0
| Upgrade from 4x4 to 4x8 landing with handrails |  | 32
|  |  | 0 | 0
| Install personal mechanial lift / platform lift based on elevation height |  | 0 | 0
| Install enclosed elevator based on elevation height |  | 0 | 0
| Additional Lift Height 5'-9' ($1.25/sqft for each additional foot of elevation) |  | 0 | 0
| Additional Lift Height 10'-13' ($1.50/sqft for each additional foot of elevation) |  | 0 | 0
| Additional Lift Height 14'-17' ($1.75/sqft for each additional foot of elevation) |  | 0 | 0
Note on B78: JH: